## Sprint 2 (with Hrs Burndown)
Sprint | # Team Members | 4 | Used for hours burn down (not as many teams do this these days)
| # Hours in 1 work day | 8 | Used for hours burn down (not as many teams do this these days)
| # Days in this sprint | 6 | Total number of work days in Sprint (exclude public holidays etc)
Hours | Day | 1 | 2 | 3 | 4 | 5 | 6
| Available | 192 | 160 | 128 | 96 | 64 | 32
| Task Hrs Remaining | 180 | 145 | 122 | 105 | 65 | 30